## Sheet1
IF Lead | Number | IF Partner | Date of Identification | Internal / External | Title | Revision | Date | Interface Description | Drawing Package | Safety Critical? | Status | Distribution | Comments | Signed by IM
RST | 0012 | TES | 12/08/09 | Int | Contact interface between OCS and Rolling Stock Vehicle pantograph | 02 | 12/16/09 | OCS designers need pantograph dimensions and physical criteria as an input to the OCS design |  | N | Closed | Roger Wilson, Gareth Rees, RST group, Peter Strange | Interfleet have provided a Pantograph criteria table. Now updated with Hyundai Rotem drawing and detail
TWK | 0018 | RST | 12/11/09 | Int | Trackwork design for ballast depths, tie spacing etc needs input from Rolling Stock | 01 | 12/11/09 | trackwork design for ballast depths, shoulder dimensions, tie spacing etc needs input from Rolling Stock re: vehicle weight and loadings |  | N | Closed | Roger Wilson, Reddy Chidananda, | vehicle weights now confirmed
RST | 0029 | CIV | 12/11/09 | Int | Rolling stock vehicle Dynamic Kinematic Envelope (DKE) detail to be confirmed | 02 | 12/16/09 | Rolling stock supplier to confirm DKE of vehicle for civil structures to check clearances. Also includes Station and Trackwork TWGs |  | N | Closed | Tom Flick, Michael Lipinski, RST TWG | action required when rolling stock vendor selected
RST | 0036 | TWK | 12/21/09 | Int | Vehicle wheel to rail interface | 01 | 12/21/09 | Vehicle wheel to rail interface study required to optimise wheel profile and rail profile for maximum life |  | N | Closed | Roger Wilson, Reddy Chidananda, Jim Devine, Joe Ferretti | Study will be done in detail design phase. Overview and strategy to be determined during proposal phase. See NEW interface with TTCI study!!
RST | 0040 | TES | 01/11/09 | Int | Vehicle data - power loadings | 01 | 01/11/09 | regenerative power and power consumption, weights, velocity, acceleration and braking characteristics required for power calculations and design |  | N | Closed | Roger Wilson, Gareth Rees, Chris Heald, Peter Strange, Reddy Chidananda | Interface logged and in discussion
RST | 0041 | STR | 01/11/09 | Int | Vehicle data - weight | 01 | 01/11/09 | vehicle data, weight, loadings etc needed for structures design |  | N | Closed | John Heffley, John Broadus, Chris Heald, Peter Strange, Reddy Chidananda | Interface logged and in discussion
RST | 0042 | CIV | 01/11/09 | Int | Vehicle data - weight | 01 | 01/11/09 | vehicle data, weight, loadings etc needed for track bed design |  | N | Closed | Tom Flick, Michael Lipinkski, Chris Heald, Peter Strange, Reddy Chidananda | Interface logged and in discussion
RST | 0115 | DUS | 2010-11-30 | Ext | Interface between DUS structural design and DTP/HR rolling stock. | 01 | 2010-11-30 | DUS Yard to DTP/HR rolling stock interface. | DTP OCS prelim Dwgs & DUS Dwgs | N | Res | P. Strange, D. Center (Aecom) | This is the high-level line item.
RST | 0115a | DUS | 2010-11-30 | Ext | Interface coordination between DUS and DTP for the Bump Posts for Tracks 1 to 3 and 6 to 8. | 01 | 2010-11-30 | The DUS design team was to work with Kiewit to provide a proposed design and vendor. Coordination required with DTP to include the proposed "type" (hydraulic vs. friction slide) as well as HR interface with the vehcile's autocoupler. | DTP OCS prelim Dwgs & DUS Dwgs | N | Res | P. Strange, D. Center (Aecom) | Bob Fauvelle provided report from the bumping post supplier during a meeting held the week of November 1-5.
RST | 0115b | DUS | 2010-11-30 | Ext | Interface coordination between DUS and DTP to resolve the Horizontal difference between the DUS designed Platform edge and the DTP/HR vehicle side for Tracks 1 to 3 and 6 to 8. | 01 | 2010-11-30 | The RTD Design Criteria for DUS platform design has defined the platform horizontal gap to be ADA compliant (less than 3"), and for the Platform hard edge to be 5'-7" from track centerline. The HR vehicle is approx. 5' wide from carbody centerline which leaves a 7" gap to be resolved. | DTP OCS prelim Dwgs & DUS Dwgs | N | Res | P. Strange, D. Center (Aecom) | The HR vehicle team is currently working on the vehicle dynamic envelope - worst case scenarios. With this information, DTP will best be able to determine a final gap and propose how to make up the difference.
RST | 0115c | DUS | 2010-11-30 | Ext | Interface coordination between DUS and DTP to resolve the Vertical difference between the DUS designed Platform edge (50-1/2") and the DTP/HR vehicle (51") for Tracks 1 to 3 and 6 to 8. | 01 | 2010-11-30 | The RTD Design Criteria for DUS platform design has defined the platform vertical height above top of rail (ATOR) to be ADA compliant (within +/- 5/8"). The HR vehicle finished floor is 51" ATOR. | DTP OCS prelim Dwgs & DUS Dwgs | N | Res | P. Strange, D. Center (Aecom) | Given that the HR vehicle has a minor dynamic movement during passenger access/egress, and that the air suspension will endeavor to retain a 51" height during passenger access/egress, the team's resolution was to leave the platform height and vehicle heights unchanged. This design criteria will be carried over for all DTP designed station platforms including DIA. It is recommneded that this design criteria be included for all future stations (i.e., the so-called "Gateway Stations" on the East Corridor.) Decision made prior to 29 Oct 2010.
COM | 0118 | RST | 2010-12-03 | Int | WiMAX antenna requires RF and mechnical interfaces and mounting on Rolling Stock vehicle | 01 | 2010-12-03 | WiMax antenna mechanical and RF interfaces to be defined with Rolling Stock team |  | N | Res | Blake Russo, Bob Fauvelle, Steve McQuilkin, Jena Montgomery | Definition and resolution tbd
COM | 0120 | RST | 2010-12-03 | Int | Rolling Stock onboard Communications Architecture needs to be IP-based | 01 | 2010-12-03 | The communications system is to be IP based.Remote devices such as CCTV cameras will have unique IP addresses to allow selection and routing of data.This will include the onboard system |  | N | Def | Blake Russo, Bob Fauvelle, Steve McQuilkin, Jena Montgomery | Resolution steps tbd
CRMF | 0125 | RST | 2010-12-27 | Ext | CRMF overhead cranes interface with rolling stock when positioned on hoists in fully raised position. | 01 | 2010-12-27 | CRMF overhead cranes interface with rolling stock when positioned on hoists in fully raised position. The sum of the hoist height, vehicle height (pantograph in lowered position) must be less than the height of the overhead crane hooks in the fully raised position. The dimensions for the hoist and crane need to be obtained by the Design-Built team. The car height dimension will be supplied by the Rolling Stock team. This interface needs to be coordinated early during the shop structural design. | DTP Proposal | Y | Ident | B. Fauvelle, PCI
CRMF | 0126 | RST | 2010-12-27 | Ext | CRMF overhead cranes interface with rolling stock and the shop mezzanine level - pantograph shop. | 01 | 2010-12-27 | CRMF overhead cranes interface with rolling stock when positioned adjacent to the mezzanine pantograph shop. When lifting a pantograph or HVAC unit off of the top of a vehicle, the sum of the crane gear, plus a jig or lifting straps, plus the pantograph or HVAC unit must allow for appropriate clearance with the finished floor level of the mezzanine. The dimensions/layout (including railings/walls) for the mezzanine, jigs/straps, and crane need to be obtained by the Design-Built team. The car height, pantograph and HVAC unit dimensions will be supplied by the Rolling Stock team. This interface needs to be coordinated early during the shop structural design. | DTP Proposal | Y | Ident | B. Fauvelle, PCI
RST | 0133 | TES | 2010-12-27 | Int | Interface between Rolling Stock and TES, min., max. and nominal voltage requirements on both sides. In the future, this discussion should also include frequency compatability, and power requirements for equipment on board at the CRT system limits. | 01 | 2010-12-27 | Interface between Rolling Stock and TES, min., max. and nominal voltage requirements on both sides. Discussions for each of the parameters above as well as frequency compatability, power requirements and performance curves at system limits (for example at DIA) have started as of this writing. | DTP Proposal | Y | Def | R. Wilson, H. Sarma, P. Strange, B. Fauvelle
COM | 0136 | RST | 2010-12-03 | Int | Communications to Rolling Stock Interfaces | 01 | 2010-12-03 | Onboard systems to be IP based to interface with Wayside design. |  | N | Def | Blake Russo, Robert fauvelle
COM | 0137 | RST | 2010-12-03 | Int | Communications to Rolling Stock Interfaces | 01 | 2010-12-03 | Power Supply interface for Radio equipment to be confirmed |  | N | Def | Blake Russo, Robert fauvelle
COM | 0138 | RST | 2010-12-03 | Int | Communications to Rolling Stock Interfaces | 01 | 2010-12-03 | OCC and SCC PA interface to onboard PA system |  | N | Def | Blake Russo, Robert fauvelle
COM | 0139 | RST | 2010-12-03 | Int | Communications to Rolling Stock Interfaces | 01 | 2010-12-03 | Vehicle mounted antenna to wayside antenna location interface |  | N | Def | Blake Russo, Robert fauvelle
COM | 0140 | RST | 2010-12-03 | Int | Communications to Rolling Stock Interfaces | 01 | 2010-12-03 | Voice Radio and other antenna mechanical and RF interfaces to vehicle |  | N | Def | Blake Russo, Robert fauvelle
CRMF | 0141 | RST | 2010-12-30 | Int | The Hyundai Rotem team requests information on the tightest "S" shaped curvature of track in the yard. | 01 | 2010-12-30 | As part of vehicle integration with the track, the Hyundai Rotem team requests informatin on the tightest "S" shaped curvature of track in the yard. |  | N | Closed | W. Lynch, B. Fauvelle, D. Center (Aecom) | Information requested in Jan. 2011, all information provided to HRU by first week of Feb 2011. Issue closed
RST | 0142 | COM | 2011-01-04 | Int | Rolling Stock - Conducted Emissions limits on the running rail | 01 | 2011-01-04 | Per section 2.6.1.2 and 2.6.1.4 of Attachment 7 Part C, the train shall comply with following conducted emission limits on the running rails so that train shall be compatible with trackside signaling system such as track circuit and cab signal. |  | N | Def | P. Strange, B. Fauvelle, B. Russo | Therefore, Hyundai Rotem needs to know what are exact frequency ranges and which will be used for signaling system.
RST | 0146 | STN | 2010-12-27 | Int | Interface between Vehicle floor at door entry and platform to meet ADA level boarding requirements | 01 | 2010-12-27 | Interface between the Vehicle door threshold and the platform has to meet the ADA level boarding criteria of ±⅝" vertical tolerance and 3" max horizontal gap | DTP Proposal | N | Res | P.Strange, R.Fauvelle, Anne Herzenberg, Roger Wilson, Donn Hogan, Steve McQuilkin
RST | 0155 | CIV | 2011-02-08 | Int | The height from the finished floor to bridge structures and track (ballast or direct fixation types) is greater than 58 inches. Access/egress will be needed for train crew at the CRMF as well as passengers during emergency egress. | 01 | 2011-02-08 | Preliminary discussions indicate that steps and grab irons will be considered for the vehicle design. |  | N | Ident | B. Fauvelle
RST | 0174 | O&M | 2011-02-02 | Int | Vehicle Monitoring & Diagnostic System (MDS) to Vehicle Maintenance Management System | 01 | 2011-04-01 | Vehicle MDS transactions will be collected in a file or database ("data pool") provided by Rotem. Need to design interface between that data pool and the Maintenance Management System so that Service Requests can be generated and troubleshooting/repairs completed. |  | N | Ident | S. Altshuler, J. Buckingham, B. Fauvelle | Design of data pool required so that import of information to maintenance can be designed.
RST | 0185 | TES | 2011-06-29 | Int | Vehicle Power Factor for TES Load Flow Study | 01 | 2011-06-29 | Vehicle Power Factor value calculation and circuit diagram required by TES for the Load Flow Study |  | N | Res | R.Fauvelle, I Simoes, A.Zvevchenko, IC Kim | Data being reviewed
CRMF | 0202 | RST | 2011-10-27 | Int | Bench Test Equipment (BTE) being provided for the new Hyundai Rotem vehicle needs to be located in the CRMF with proper utility services available. | 00 | 2011-10-27 | To provide adequate space and utility support in the CRMF for any and all BTE to be provided, a complete list of the BTE is requested with sizes, weights, and utility information. |  | N | Ident | L. Mallory, D. Cross
CRMF | 0203 | RST | 2011-10-27 | Int | Cad drawings of the Denver Hyundai Rotem vehicle for use in preparation of CRMF drawings. | 00 | 2011-10-27 | CAD drawings of the vehicle would facilitate the preparation of equipment drawings for the construction of the CRMF. |  | N | Ident | L. Mallory, D. Cross
CRMF | 0204 | RST | 2011-10-27 | Int | List of capital spares being provided with the new Denver Hyundai Rotem vehicle. | 00 | 2011-10-27 | To verify that adequate storeroom space is available in the new CRMF, this information is required. GF has been told verbally that this information is available from Hyundai-Rotem. |  | N | Ident | L. Mallory, D. Cross
CRMF | 0205 | RST | 2011-10-27 | Int | The CRMF car hoisting system for the Hyundai Rotem vehicles will include body stands to support the vehicle body when trucks are removed. | 00 | 2011-10-27 | To correctly specify the car hoisting equipment, dimensions of the locations of the body jacking pads are required as well as a detail of the pad with pad dimensions. |  | N | Ident | L. Mallory, D. Cross
CRMF | 0206 | RST | 2011-10-27 | Int | Type of fluids as well as properties required for servicing of the Denver Hyundai Rotem Vehicle. | 00 | 2011-10-27 | To design and specify the CRMF fluid dispensing systems, the type as well as the associated MSDS sheet for each fluid is required. GF has been told verbally that this information is available from Hyundai-Rotem. |  | N | Ident | L. Mallory, D. Cross