## Sheet1
Hyundai Rotem - Denver RTD Action Item List
No. | Comment | Status | Person in charge | Issued Date | Due Date | Woojin Response
1001 | HR/Woojin to provide a user manual for the PA/VMS programming software as well as a sample spreadsheet that contains the data needed for the initial programming. (RS-MM-084-8) | Open | I.C. Kim - HR | 12/12/2011 | 1/6/2012 | ⇒ Woojin will provide the user manual for the PA/VMS programming software as well as a sample spreadsheet that contains the data needed for the initial programming until Jan. 6th.
1003 | HR/Woojin to send to DTP the wayside text message ICD when complete. (RS-MM-084-9) | Open | I.C. Kim - HR | 12/12/2011 | 1/6/2012 | ⇒ Woojin will provide the ICD before Jan. 6th.
1005 | Leo Jeon to provide a block diagram sketch of the MDS to wayside download scope and functionality. (RS-MM-084-15) | Open | I.C. Kim - HR | 12/12/2011 | 1/6/2012 | ⇒ Woojin will design a block diagram sketch of the MDS and provide it until Jan. 6th.
1012 | Leo Jeon to provide a step-by-step procedure for making PA announcement using the DPO, DPH and gooseneck microphone. Leo also to look into adding a speaker select pushbutton on the left side of the cab to allow for left handed PA announcements while the vehicle is in motion. | Open | I.C. Kim - HR | 12/19/2011 | 12/30/2011 | ⇒ (Woojin will include the detailed operating scenario in the step-by-step procedures document. Please refer to the document when we submit.) <Jan. 13th>
1016 | HR & Woojin to determine if a cold start requires the operator to select the route number again, whether the time between cold start and warm start is adjustable and whether the communications system could acquire operator login and intended route data from another system. (RS-MM-085-2) | Open | I.C. Kim - HR | 12/13/2011 | 1/13/2012 | ⇒ Woojin will prepare the respond before Jan. 13th.
1017 | HR to define exactly what communications & CCTV equipment HR will provide (hardware and software) for installation at the CRMF. (RS-MM-085-3) | Open | I.C. Kim - HR | 12/13/2011 | 1/13/2012 | ⇒ Woojin will supply only the Software (schedule editor).
1021 | HR & Woojin to perform a new simulated analysis for the sound pressure of interior speakers to provide a better and more accurate result to RTD/DTP/DTO. (RS-MM-085-15) | Open | I.C. Kim - HR | 12/13/2011 | 2/9/2012 | ⇒ Woojin will provide the simulation result for the Denver project. (We have been designing the location of the speaker according to the SEPTA’s simulation result. However, we would like to perform a new simulation procedure to provide a better and more accurate result to RTD.) Woojin will provide the result at early February.
No. | Comment | Status | Person in charge | Issued Date | Due Date | Woojin Response
1023 | HR/Woojin to provide the expected life of the exterior speaker. (RS-MM-085-21) | Open | I.C. Kim - HR | 12/13/2011 | 12/30/2011 | ⇒ The expected life of the exterior speaker is about 5 years.
1024 | HR/Woojin to evaluate changing the DPH to include only a microphone jack and hanger. The speaker controls could be removed. What is the effect to the quoted change order cost? (RS-MM-085-23) | Open | I.C. Kim - HR | 12/13/2011 | 1/13/2012 | ⇒ Woojin will prepare the respond before Jan. 13th.
1025 | HR & Woojin to provide the step-by-step procedure of the activation and deactivation of the DPO, DPH and gooseneck microphones. (RS-MM-085-24) | Open | I.C. Kim - HR | 12/13/2011 | 1/13/2012 | ⇒ (Woojin will include the detailed operating scenario in the step-by-step procedures document. Please refer to the document when we submit.) <Jan. 13th>
1026 | HR/Woojin to propose a solution that will allow for the operator to initiate and make PA announcements while in operation by using only their left hand. (RS-MM-085-25) | Open | I.C. Kim - HR | 12/13/2011 | 1/13/2012 | ⇒ (Woojin will include the detailed operating scenario in the step-by-step procedures document. Please refer to the document when we submit.) <Jan. 13th>
1027 | HR/Woojin to provide the analysis and assumptions used to calculate the Woojin RAM data. (RS-MM-085-30) | Open | I.C. Kim - HR | 12/13/2011 | 1/6/2012 | ⇒ Woojin will provide the Wooin RAM data before Jan. 6th.
1028 | HR/Woojin to provide an ICD that includes all detailed questions and information requests for the wayside communications design team to respond to. (RS-MM-085-32) | Open | I.C. Kim - HR | 12/13/2011 | 1/6/2012 | ⇒ Woojin will provide the ICD before Jan. 6th.
1029 | HR/Woojin to submit the revised communications system software documents before software development begins in January. (RS-MM-085-34) | Open | I.C. Kim - HR | 12/13/2011 | 12/28/2011 | ⇒ Woojin will submit the revised communications system software documents as soon as possible.